EUROPEAN COMMISSION

DIRECTORATE-GENERAL
EDUCATION  AND CULTURE

LEONARDO DA VINCI PROGRAMME

PILOT PROJECTS, LANGUAGE COMPETENCES, TRANSNATIONAL NETWORKS AND REFERENCE MATERIAL

ADMINISTRATIVE AND FINANCIAL HANDBOOK

for Promoters

CL/21a/99Rev4

TABLE OF CONTENTS

PURPOSE OF THE ADMINISTRATIVE AND FINANCIAL HANDBOOK	4

I. SUBMISSION OF PROPOSALS	5

II. CONTRACT FORMALITIES                                                                                                     6

1. DESCRIPTION OF THE CONTRACT FORM	6

2. FORMAL RULES FOR ACCEPTANCE OF THE FORM	6

3  BUDGETARY INFORMATION	7

III. OPERATIONAL MANAGEMENT OF THE PROJECT	9

III.1.	AMENDMENT OF THE AGREEMENT	9

III.1.1.	AMENDMENT OF THE AGREEMENT AND ITS ANNEXES	9

III.1.2.	AMENDMENT OF THE PROJECT DESCRIPTION	11

III.1.3.     AMENDMENT OF THE BUDGET                                                                                           11

III.2. ELIGIBILITY	11

III.2.1. 	GENERAL REMARKS	11

III.2.1.1.	 Eligibility of expenditure	11

III.2.1.2.	 Duration of the project	12

III.2.2. 	PERSONNEL COSTS	12

III.2.3. 	TRAVEL AND SUBSISTENCE COSTS	13

III.2.4. 	EXPENSES RELATING TO INFORMATION AND COMMUNICATION TECHNOLOGIES

14

III.2.5.	PRODUCTION COSTS	15

III.2.6. 	OVERHEADS	15

III.2.7. 	OTHER COSTS	15

III.2.8.	SUBCONTRACTING COSTS	16

III.3. FINANCIAL MANAGEMENT OF THE PROJECT BY THE CONTRACTOR	17

III.3.1.	GENERAL REMARKS	17

III.3.2.	BANK ACCOUNT	17

III.3.3. 	ACCOUNTING SYSTEM/INTERNAL CONTROL	17

III.3.4.	VAT, CUSTOMS DUTIES AND OTHER TAXES ON GOODS AND SERVICES	17

III.3.5.	EXCHANGE RATES	17

III.3.6.	PAYMENT OF THE GRANT 	19

IV. REPORTS	19

IV.1. GENERAL REMARKS	19

IV.2. FORMAL REQUIREMENTS FOR THE ACCEPTANCE OF REPORTS	19

IV.3. INTERIM REPORTS	20

IV.3.1. 	GENERAL REMARKS	20

IV.3.2. 	ACTIVITY/RESULTS REPORT	20

IV.3.3. 	FINANCIAL REPORT	20

IV.4.  FINAL REPORT	20

IV.4.1. 	GENERAL REMARKS	20

IV.4.2. 	ACTIVITY/RESULTS REPORT	21

IV.4.3. 	FINANCIAL REPORT	21

IV.4.4. 	EVALUATION AND MONITORING	21

IV.4.5. 	CALCULATION OF THE FINAL COMMUNITY GRANT	21

V.	AUDITS	25

V.1.	PURPOSE	25

V.2.	DOCUMENTS REQUIRED	25

V.2.1.	GENERAL REMARKS	25

V.2.2.	PERSONNEL COSTS	26

V.2.3.	TRAVEL AND SUBSISTENCE COSTS	26

V.2.4.	COSTS IN CONNECTION WITH COMPUTER AND AUDIOVISUAL EQUIPMENT	26

V.2.5.	PRODUCTION COSTS	26

V.2.6.      OVERHEADS	26

V.2.7.      OTHER COSTS	26

V.2.8.     SUBCONTRACTING COSTS   	26

V.3. FINDINGS AND OUTCOME	27

VI.	 ANNEX I

INTERNATIONAL STANDARD CLASSIFICATION OF OCCUPATIONS	28

PURPOSE OF THE ADMINISTRATIVE AND FINANCIAL HANDBOOK

The Handbook is intended to serve both as an aid for Contractors  and as a management tool.  It is intended to:

- help Contractors to run projects efficiently;

- clarify various matters arising from the Agreement and its annexes;

- provide practical information to which Contractors may refer at the various stages of the project;

- provide guidance for Contractors on handling the financial side of projects in such a way that financial statements can be readily drawn up;

- ensure the smoothest possible relations between the parties involved by setting out an operational framework for the project.

Financial management of a project is an aid to ensuring that the best results/products are produced at a moderate cost. Since activities almost always give rise to costs, the main aim is thus to identify the results/products achieved, their quality and their cost. This key concept of the quality/cost ratio will be central to evaluation of the project.

The rules outlined in the Handbook apply to all the funds administered under Leonardo Da Vinci projects. They form a set of good practices which project managers should try to follow as closely as possible. However, since a wide range of situations may be encountered, other management procedures may be justified, provided that:

- they are transparent;

- they do not run counter to the general philosophy of the Leonardo Da Vinci programme or the normal rules of good management;

- they are explained when submitting reports.

Definition of terms recurring in this handbook:

Promoter: any institution or body, private, public or semi-public declaring its intention, in accordance with the set procedures, to submit a proposal for transnational co-operation within the scope of the programme. The promoter organisation will become the contractor when the proposal is accepted and the project starts.

Partner: any institution or body, private, public or semi-public, which is associated with the presentation of a proposal and which has signed a letter by which it undertakes, according to the agreed arrangements, to contribute to the implementation of the project.

Contractor: any institution or body, private, public or semi-public, which on behalf of the other partners associated in the request for financial support from the programme, is responsible for presenting the proposal, as the promoter organisation, and which therefore, if it is selected, is liable under the contract and is responsible for the day-to-day co-ordination and management of the project and for distributing the Community funds allocated for this project. Day-to-day co-ordination and management can be delegated to a co-ordinator, in which case the delegation arrangements must be clearly spelt out.

Co-ordinator: this is the institution or body selected among the members of the transnational partnership to be responsible for the necessary co-ordination and day-to-day management tasks at the implementation stage. This institution or body may differ from the contractor.

# I. SUBMISSION OF PROPOSALS

Applicants whose pre-proposal has been selected will be invited to complete and submit the application form.

The financial tables to be filled out by the Contractor are:

- a breakdown of estimated costs by phase and by type of cost

- a breakdown of personnel needs and estimated expenses by Partner

- a breakdown of the costs by type of cost and by Partner

- funding estimates by type of cost and by Partner.

# Breakdown of the estimated costs by phase and by type of cost

The applicant must specify the various phases of the project and estimate the personnel, operational and subcontracting costs for each.

Breakdown of personnel needs and estimated expenses by Partner

Five  categories of personnel are to be distinguished:

a) 	ISCO 1 : legislators, senior officials and managers,

b)	ISCO 210, 220 or 240 : professionals,

c)	ISCO 230 : teachers, trainers

d)	ISCO 3 : technicians and associate professionals,

e)  ISCO 4 : clerks.

For each category, state the estimated number of working days and daily labour costs.

# Breakdown of the costs by type of cost and by Partner

For the project as a whole, the applicant, with the assistance of the Partners, must estimate what costs of each type the promoter and each Partner will incur.

- Personnel costs

Transfer the total amount of previous table

- Operating costs

a) Travel and subsistence costs

In addition to the total for each Partner, the tenderer must attach an explanation of the basis of calculation, viz. the number, venues and dates of meetings and trips planned.

b) 	Information and communication technology costs

c)	production costs

d)	overheads

e)	other costs

Section III.2 explains what costs are eligible for headings a, b, c, d and e.

- Subcontracting costs.

# Breakdown of funding estimates by Partner

The tenderer must state each Partner's expected sources of funding, which must match the letters of intent sent by the Partners.

II. CONTRACT FORMALITIES

If the project submitted is sufficiently detailed, the budget is realistic and acceptable in the light of Community standards and the subsidy granted is the same as that requested by the tenderer, the contracting phase can be limited to a simple exchange of information not contained in the application form, such as bank details and the articles of association of the tenderer. This information must be sent when the signed contract is returned.

II.1. DESCRIPTION OF THE CONTRACT FORM

Before the Agreement is drawn up, the Contractor must complete a contract form and return it to the National Agency.

This form is in two parts.

The first gives details of the project, summarising all the information on the Partnership and project content which will be included in the Agreement, such as:

- name and details of the members of the Partnership, with the commercial register and VAT identification numbers for those members who have them;

- project title and acronym.

Contractors must indicate legibly, in block capitals, any changes that they may wish to make to these details. As regards the Partnership, they must also specify the official names (company names) - written out in full - of all the project Partners, as given in their articles of association, and the commercial register and VAT identification numbers for those Partners who have them.

The second part, which must be completed by the Contractor according to the rules set out below, contains:

- a factual and detailed description of the impact any reduction in the total cost would have on the project activities and/or results;

- a sheet with bank particulars;

- a budget proposal based on the total updated cost of the project;

- an form for acknowledgement of receipt;

- a model letter of intent for Partners;

- a signature form, on which the Contractor must indicate, if necessary, the names and titles of the various persons who are authorised under the terms of the articles of association to enter into commitments on behalf of the Contractor and thus to sign reports and all official documents; these persons must write their signatures opposite their names.

II.2. FORMAL RULES FOR ACCEPTANCE OF THE FORM

So that the form can be used for the preparation of the Agreement and the latter can be sent to the Contractor as soon as possible, the following formal requirements must be satisfied:

- An original copy of the form must be sent to the National Agency3 (photocopies will not be accepted under any circumstances).

- The form must bear the original signature of the representative legally entitled to sign  of the contracting organisation. The name of this representative and his position/title within that organisation must be given below the signature, which must be accompanied by the organisation’s official stamp. The National Agency must be explicitly informed of any subsequent change of legal representative.

- The whole of the form (i.e. all its pages) must be returned, duly completed and signed in the appropriate places.

- Any change to the pre-printed data in the form must be clearly indicated and will be checked before acceptance.

- The bank particulars sheet, details from which will be included in the Agreement, must be correctly completed and duly signed by the organisation’s legal representative or financial director. The sheet must also indicate the bank account to which the Leonardo da Vinci grant is to be paid and which must be:

- 	in the name of the contracting organisation (personal accounts are not acceptable under any circumstances);

- 	where possible, specific to the project (in the case of a general account, the Contractor must set up an analytical accounting system allowing both expenditure and revenue connected with the project to be identified);

-	as far as possible in euros (this is strongly recommended);

-	in a Member State of the European Union or the European Economic Area or in one of the associated countries participating officially in the programme.

- The revised budget, including details of co-financing, must be entered correctly in the appropriate table.

- Letters of intent from the Partners listed in the project details section of the form must be sent with the form if they have not already been sent with the application and must meet the following requirements:

- They must be original letters written on the organisation’s letter-headed paper.

- They must be signed by a representative legally entitled to sign and bear the organisation’s stamp.

- They must attest to a real commitment from the Partner organisation and specify the role that this Partner will play in carrying out the project.

- They must clearly state the amount of the Leonardo da Vinci grant that the organisation will receive, and the amount of co-financing it will provide for the project, with a breakdown by funding source. If the figures given in previously supplied letters of intent are incomplete or are no longer up-to-date, new letters of intent containing up-to-date figures must be sent.

- They must clearly indicate the title and number of the project.

- A copy of the contracting organisation’s articles of association must be annexed to the form.

# II.3.	BUDGETARY INFORMATION

On the basis of the budget submitted by the promoter, the Commission, when examining and selecting proposals,  with the assistance of external experts and assessments from the participating States, will determine the estimated eligible expenditure in the light of the project aims and in accordance with the rules on eligibility and financial evaluation applying at Community level.

This estimated eligible expenditure will be the total acceptable cost which the Commission will take into consideration for execution of the project:

On the basis of the estimated eligible expenditure, the Commission, in consultation with the Leonardo da Vinci Committee, will determine the amount of Community support to be provided for the project. This will initially be expressed as a total amount, which must comply with the ceilings set by the Council Decision, both in absolute terms and as a percentage of the estimated eligible expenditure. Secondly, the amount of support will be broken down as follows:

- a lump sum for personnel costs

- the funding levels for the various budget headings for operating and subcontracting costs.

The following imaginary outline budget may serve as an example:

|  | Budget submitted by the promoter | Estimated eligible expenditure | Community support | % |
| --- | --- | --- | --- | --- |
| A. Personnel costs |  |  |  |  |
| ISCO 1 | 52 350 | 50 705 |  |  |
| ISCO 210, 220 or 240 | 7 100 | 6 920 |  |  |
| ISCO 230 | 2 000 | 2 000 |  |  |
| ISCO 3 | 8 800 | 8.360 |  |  |
| ISCO 4 | 20 250 | 20 250 |  |  |
| Sub-total I | 90 500 | 88 235 | 57 000 |  |
| B. Operating costs |  |  |  |  |
| 1. Travel | 34 500 | 31 500 | 31 500 | 100% |
| 2. ICT | 20 000 | 20 000 | 20 000 | 100% |
| 3. Production | 5 000 | 5 000 | 5 000 | 100% |
| 4. Overheads | 13 500 | 13 500 | 0 | 0% |
| 5. Others | 0 | 0 | 0 | 0% |
| Sub-total II | 73 000 | 70 000 | 56 500 | 80.7% |
| C. Subcontracting costs |  |  |  |  |
| 1. Translation | 25 000 | 20 000 | 20 000 | 100% |
| Sub-total III | 25 000 | 20 000 | 20 000 | 100% |
| Total project cost | 188 500 | 178 235 | 133 500 | 74.9% |

In this example, the promoter, having sent an estimate of € 188 500, will be told  when the contract forms are returned that:

- the estimated eligible expenditure, given the project aims and the means to be used, has been assessed at € 178 235;

- the total Community grant, subject to achievement of  the project aims and compliance with the eligibility rules, will amount to € 133 500, i.e. 74.9% of the estimated eligible expenditure;

- the lump sum for personnel costs, if the project aims are achieved, will be € 57 000;

- travelling expenses will be 100% funded up to a maximum of € 31 500;

- ICT costs will be 100% funded up to a maximum of € 20 000;

- production costs will be 100% funded up to a maximum of € 5 000;

- overheads are assessed at € 13 500, but will attract no Community funding;

- translation costs will be 100% funded up to a maximum of € 20 000.

III. OPERATIONAL MANAGEMENT OF THE PROJECT

# III.1.	AMENDMENT OF THE AGREEMENT

# III.1.1	Amendment of  the Agreement and its annexes

If the smooth running of the project so requires, the Contractor may have the Agreement amended  during its term, even after it has been signed, subject to the formalities described below. The Contractor must send the National Agency a written request for such amendment, dated and signed by its legal representative. The National Agency6 will examine, in each case, whether or not this amendment should be set out in a formal endorsement, and will inform the Contractor of its decision.

The formal steps to be taken are as follows:

- If a basic change is to be made in the general performance of the work programme, the development of training products/results or the planned dissemination arrangements, the Contractor must send a prior request for authorisation to the National Agency6, explaining the reasons for the proposed change.

- If a Partner withdraws, provided that this does not alter the nature and transnational character of the project, the Contractor must send the National Agency6:

-	an explanation proving that the partner’s withdrawal does not alter the transnational character of the project;

- 	the original of the official letter, dated and signed by the representative legally entitled to sign of the Partner organisation withdrawing from the project, giving notice of its withdrawal and stating the reason(s);

- 	a statement of the status of the work carried out by the withdrawing Partner, of the rights that the latter has acquired in respect of the product/result of the project and of the funds that the Partner has received, as well as the amount repaid, if any;

- 	official evidence of termination of the contract with the withdrawing Partner (e.g. a copy of the letter of termination) and, where appropriate, of the repayment of funds.

The National Agency6 will notify its formal acceptance or non-acceptance of the documents received and will authorise or not the withdrawal of the Partner.

Evidence of expenditure by the withdrawing Partner must be kept and must be available on request. The unspent part of the budget earmarked for this Partner may, with the prior approval of the Agency6, be reallocated to the member(s) of the Partnership who are to take over the tasks of the withdrawing Partner.

- If a new Partner joins, the Contractor must send the National Agency6:

- 	the original of the official letter of commitment, dated and signed by the representative legally entitled to sign of the organisation wishing to join the project;

- 	the information sheet for new Partners;

- 	together with the next report, a copy of the contract concluded between the Contractor and the new Partner (see Annex IV.3 to the Agreement).

The National Agency6  must notify its assent to the new Partner's joining.

- If a Partner is replaced by another Partner, the Contractor must send the National Agency6 all the documents required under both the above sections.

- If there is a change of contracting organisation (but the other Partners remain the same and the original and new contracting organisations are of the same nationality), and provided that this does not alter the nature or aims of the project and is approved by all the Partners and the National Agency, the following procedure must be followed:

- The withdrawing Contractor must send the National Agency7 an official letter, dated and signed by its representative legally entitled to sign, in which it stands down as Contractor, states its reasons and specifies whether or not it is joining the list of Partners or is withdrawing from the project completely (in which case, it must also comply with the requirements for withdrawal of a Partner).

- The Contractor must attach a dated and signed statement of the current status of work and expenditure and of the funds to be transferred to the new Contractor.

- A report of the withdrawing Contractor's activities and expenditure, with all supporting documents, must be sent to the new Contractor.

- The latter must send the National Agency7 an official letter, dated and signed by a legal representative, in which it approves the report from the former Contractor and undertakes to act as Contractor and to pursue such activities from that date, and must attach the information sheet for new Contractors and the bank particulars sheet, duly completed and signed.

- An official document substantiating the transfer of funds (e.g. a transfer order signed by the bank) and the agreement of the former and new Contractors to this transfer must be sent to the National Agency7.

The former and new Contractors should set out the above points in an agreement, duly dated and signed by each organisation’s representative legally entitled to sign, and to send a copy to the National Agency7.

- Each Partner must notify its agreement to the change of Contractor by means of the original of an official letter dated and signed by its legal representative. These letters must be attached to the documents mentioned above.

The former Contractor remains liable for management during its period as Contractor, up to the end of the period of legal liability, i.e. five years after the end of the project.

- If there is a change of co-ordinating organisation (but the Partnership remains the same), the Contractor must send the National Agency7 a letter accompanied by the information sheet for new Co-ordinators. If the former Co-ordinator is leaving the project completely (i.e. is not joining the list of Partners), the requirements for withdrawal of a Partner must also be fulfilled. If a new organisation is taking on the role of Co-ordinator, the procedure for admitting new Partners must also be followed.

- If there is a change in the bank account to which the Leonardo da Vinci grant is paid, the Contractor must inform the National Agency7 in a letter accompanied by a new bank particulars sheet bearing the original signature of the contracting organisation’s legal representative.

- Likewise, any request for extension of the contract period, i.e. the period during which project activities and expenditure are eligible, must be made officially by the Contractor. If this request is approved, a written reply will be sent.

# III.1.2	Amendment of the project description

Some changes may be accepted if they are justified and do not undermine the project’s nature and aims. Reasons must be given for the proposal to revise activities/results, which must be sent to the National Agency and must be approved in advance by it.

III.1.3. 	Amendment of the budget

Provided the total cost remains unchanged, changes in the amounts given for each budget heading may be acceptable if they are justified and do not undermine the project’s nature and aims. If, however, headings are to be changed simultaneously by more than 10% and € 5 000, the Contractor must send a proposal to National Agency8 in advance in the form of a new revised budget, justifying the proposed changes. This revised budget must be approved in advance by the National Agency8. The National Agency8 also reserves the right, after evaluation and financial checking, to refuse any major change that is not satisfactorily explained and to demand repayment of the portion of the grant corresponding to that change.

These budget changes may not affect the Community contribution to personnel costs, since it has been set as a lump sum and will remain unchanged throughout the course of the project.

III.2. ELIGIBILITY

III.2.1. 	General remarks

III.2.1.1.	 Eligibility of expenditure

In general, only costs meeting the following criteria are eligible for co-financing: they must relate to activities involving the Member States of the European Union and/or the European Economic Area and/or the associated countries participating officially in the programme; they must be directly connected with execution of the project in accordance with the plan of work; they must be incurred by member organisations of the Partnership; they must be actual costs, apart from the lump sums permitted by this Handbook, i.e. the actual costs incurred must correspond to payments made by the Partnership, supported by receipted invoices or accounting documents of equivalent substantiating effect. Where national taxation and accounting rules do not require an invoice to be issued, an accounting document of equivalent substantiating effect means any document produced in order to prove that the accounting entry is accurate and complies with the accounting law applying.

The general context, nature and amount of expenditure will be considered when assessing its eligibility.

Some costs will in all cases be considered ineligible, in particular:

- costs incurred in respect of, or for travel to, countries outside the European Union and the European Economic Area, with the exception of the associated countries participating officially in the programme;

- costs incurred outside the contract period;

- costs having no direct link with the project;

- unnecessarily high costs which are unsubstantiated or which are rejected by the National Agency;

- costs not covered by lump-sum provision which are not substantiated by appropriate accounting documents and which do not appear in the project’s accounts;

- costs already financed from another source, in particular by other Community funds (in cases of complementary financing, this must be clearly substantiated and explained);

- any unwarranted subcontracting costs that yield no added value for the project;

- purchases of capital assets, except in cases specifically provided for in this Handbook;

- payments to a National Agency or an intermediary for participation in the Leonardo da Vinci programme;

- contributions in kind for which there are no suitable accounting documents and which do not appear in the project accounts;

- costs of invested capital;

- provisions for possible future losses or debts;

- provisions for liquidation, termination of activities, breach of lease or social security obligations;

- provisions for contractual and moral obligations;

- amounts placed in reserve;

- debts owed;

- bad debts;

- financial costs (loan interest, exchange costs and other purely financial costs);

- costs of opening and operating bank accounts, bank transfers and other bank charges;

- fines, financial penalties and legal costs.

III.2.1.2.	Duration of the project

The project duration is that stipulated in the Agreement, i.e. the contract period. Only costs incurred as part of the project and during this period will be regarded as eligible. Costs incurred before or after will not be eligible.

Promoters who in certain circumstances are unable to achieve their aims within the specified period may submit to the National Agency12 a reasoned request for an extension of the contract period. After considering the promoter's arguments, the National Agency12 may if it sees fit agree to an endorsement to the original Agreement, extending the contract period by not more than six months. Any request for an extension of more than six months in relation to the original agreement must be approved by the Commission, but the endorsement will be issued by the National Agency12. A distinction must be made between a request for extension of the contract period, which has the effect of increasing the period within which costs are eligible and which must always be confirmed by an endorsement, and a request for an extension of the deadline for submitting interim or final reports, which may not exceed two months, involves no extension of the contract period and does not require an endorsement to the Agreement.

III.2.2. 	Personnel costs

Since personnel costs are covered by a lump sum, they need not be accounted for in the final report, the lump sum being due if the project achieves its aims. What is meant by "achieving the aims" is explained in due course.

Nevertheless, in order to draw up the budget, the tenderer and Partners will have to take account of what will be allowed as personnel costs, viz. any remuneration paid to persons attached to a member organisation of the Partnership or working regularly or recurrently for the project (whatever their status).

Personnel costs must be calculated on the basis of the actual daily salary/fee of the employee/service provider, multiplied by the number of  days worked on the project. Where applicable, this figure must include all the usual contributions paid by the employer, such as social security contributions, but must exclude any bonuses, incentive payments or profit-sharing schemes.

Ex-ante project evaluation will take account of the declared number of days required to carry out the project and the daily costs declared by each member of the Partnership. With regard to the daily personnel costs, the declared costs will be compared with the average costs for each category (ISCO1, ISCO2, ISCO3 and ISCO4) in each country taking part in the programme. Moreover the maximum permitted amounts, for a full-time day with all charges included, are in principle € 450  for ISCO1, € 300 for ISCO210-220-240 or 230, € 250  for ISCO3 and € 125  for ISCO4. If, owing to the specific features of the project, the promoter plans to include highly qualified staff whose individual rates are higher than the maxima established, he/she will have to indicate it and provide all necessary explanations when submitting his/her proposal.

For reference, the personnel categories are as follows:

ISCO 1: Legislators, senior officials and managers

ISCO 210, 220 or 240: Professionals

ISCO 230: Teachers, trainers

# ISCO 3: Technicians and associate professionals

# ISCO 4: Clerks.

When the final report is submitted to the National Agency, it will be evaluated both by that Agency13 and by an independent external expert.

The external independent experts will be designated by each Member State for the proposals coming under procedure B, and by the Commission for those coming under procedure C.

The persons carrying out these evaluations will assign an overall rating, on a scale from 0 to 10, to the project results in the light of aims stated in the proposal.

If the rating awarded by the National Agency13 or external expert lies between 0 and 4, a further evaluation must be obtained from a second independent external expert.

If this is consistent with the previous evaluations, the following action will be taken:

- for ratings between 0 and 2 inclusive, the promoter will be required to repay the grant in full;

- for ratings between 3 and 4 inclusive, the lump sum for personnel costs will be reduced by 50%;

- for ratings between 5 and 10 inclusive, the promoter will be entitled to the full lump sum, as provided by the contract.

If the evaluations differ, the National Agency13 will determine unilaterally and definitively the final lump sum for personnel costs due to the promoter.

III.2.3. 	Travel and subsistence costs

Reimbursement may be claimed under the Leonardo da Vinci programme only for journeys directly linked to the project, and relating to specific and clearly identifiable activities.

Allowable travel costs under the Agreement will be the real travel costs. The Partnership is required to use the cheapest means of travel, and its members will thus have make every effort to use Apex tickets for air travel and take advantage of reduced fares.

Expenses for car travel, where substantiated and where the price is not excessive, will be refunded as follows:

- for private vehicles: on the basis of the corresponding rail or air fare (the price of one ticket only will be reimbursed, even where several people are travelling in the same vehicle);

- for hire cars (maximum category B or equivalent) or taxis: the actual cost where this is not excessive compared with other means of travel.

Any travel to places other than those where the members of the Partnership are located must be shown to be relevant to the project.

Subsistence costs may be financed by the project, provided:

- they are reasonable in the light of local prices;

- they are calculated in accordance with the Partner organisations' internal rules, which may be on an actual cost or daily allowance basis.

They may not, however, exceed the lower of the daily rates below:

- the daily rate per person applied by the organisation to which the person travelling belongs;

- the maximum daily rate per person shown below.

| Countries participating in the Leonardo Da Vinci programme | Subsistence costs (in euros) |
| --- | --- |
| Austria | 122 |
| Belgium | 150 |
| Bulgaria | 157 |
| Cyprus | 100 |
| Czech republic | 214 |
| Denmark | 179 |
| Estonia | 129 |
| Finland | 156 |
| France | 130 |
| Germany | 127 |
| Greece | 113 |
| Hungary | 136 |
| Iceland | 183 |
| Ireland | 165 |
| Italy | 130 |
| Latvia | 174 |
| Liechtenstein | 174 |
| Lithuania | 126 |
| Luxembourg | 143 |
| Netherlands | 148 |
| Norway | 171 |
| Poland | 227 |
| Portugal | 143 |
| Romania | 185 |
| Slovak republic | 164 |
| Slovenia | 148 |
| Spain | 141 |
| Sweden | 157 |
| United Kingdom | 199 |

# III.2.4. 	Expenses relating to information and communication technologies

Computer costs will normally include all costs relating to connection time, CPU time, lines printed, consultation of or links to databases and acquisition of software, provided these costs are directly relevant to the project. Only actual costs necessary for the completion of the project can be claimed under the Agreement, provided they are duly substantiated.

Certain hardware costs (purchase, rental or leasing) may be admissible.

The Contractor, complying with the terms of  the Agreement, must then:

- give preference, when purchasing or renting, to equipment manufactured or at least assembled in a Member State of the European Union or the European Economic Area or in one of the associated countries participating officially in the programme, where such equipment is available on the market;

- compare the prices of different suppliers to see which offers the best value for money (taking account of price and quality);

- charge against the project only the cost of equipment purchased or rented during the contract period, at a rate which reflects the degree and duration of use within that period. Where equipment is purchased, the Contractor must apply an annual depreciation rate of not more than 33.33% for computer and audio-visual equipment worth less than € 10 000 and not more than 20% for equipment worth over € 10 000.

Example:

Total value of equipment purchase: € 1 000.

Assumed service life: three years (36 months).

Permissible monthly depreciation will then be € 1 000/36 = € 27.78.

Duration of the Agreement: from 1/12/1998 to 30/11/2000, i.e. 24 months.

Date of invoice: 1/5/2001.

The period of use for the project will then be not more than 19 months.

Supposing the equipment is used on a half-time basis for the project, the utilisation rate will be 50%.

The total amount payable for depreciation under the Leonardo da Vinci grant will then be:

(27.78 x 19) x 0.5 = € 263.91.

The equipment purchased must also be itemised in the organisation in which it is installed and bear an inventory number.

Contractors must abide by the principles of sound management when deciding to rent, lease or purchase equipment and must be able to justify their choice.

The overall costs of computer and audio-visual equipment must not exceed 15% of the total project cost, save in exceptional cases where duly substantiated and subject to prior authorisation.

# III.2.5.		Production costs

These are costs related to the production by a member of the Partnership of the products which are stipulated in the project aims and the costs of which are of a type which does not fall under one of the other headings.

III.2.6. 	Overheads

Overheads include the following costs, provided they are specific to the project:

- communications (fax, telephone, mail, etc.);

- photocopies;

- hire of conference or training rooms, if essential to achieving the project aims.

Under no circumstances the heading “Overheads” may cover personnel costs or any other cost covered under another heading. In addition, the  following expenditure will no be accepted in any event:

- expenditure on rent, heating, electricity, water or any other accommodation costs normally paid for by the Partnership organisations:

- structural costs with no obvious link to the project;

- office equipment.

A lump sum of not more than 7% of the total project cost (estimated budget) will be allowed as overheads.

III.2.7. 	Other costs

It may be possible for other additional or unforeseen costs not falling into any of the above categories to be claimed under the Agreement, with the consent of the National Agency, provided they are considered necessary to the proper performance of the work specified in the Agreement and involve no fundamental change in the work's scope or content.

Costs that the Contractor charges to this heading must therefore meet the following criteria:

- they must not be covered by any other budget heading;

- they must be necessary to the proper performance of the work;

- they must not involve any fundamental change in the scope and content of the work;

- they must be eligible under the Agreement;

- they must be clearly identifiable.

III.2.8.	Subcontracting costs

Any amount paid to an external party which is not part of a member organisation of the Partnership and is carrying out a specific one-off task in connection with the project must be charged against “Subcontracting costs”. (For instance, translation, interpreting and printing work carried out by organisations outside the Partnership are subcontracting costs).

These costs are admissible only if the staff of the member organisations of the Partnership does not have the skills required.

Only subcontracting costs in conformity with the Agreement are admissible. If a Partnership member enters into a subcontracting agreement, it must draw up an agreement in which the subcontractor undertakes to abide by the main Agreement concluded with the National Agency. Subcontractors shall  be located in the Member States of the European Union or the European Economic Area or in the associated countries participating officially in the programme.

Subcontracting agreements must include at least the following information:

- purpose of the agreement;

- dates on which the agreement begins and ends;

- amount to be paid;

- detailed description of the costs on which this figure is based;

- work schedule/completion phases;

- payment arrangements (one or more advance payments, staggered payments, etc.);

- clauses in respect of non-performance or late completion.

It is not permissible to subcontract all the project activities, as this would distort the concept of the Partnership. For this reason, the Contractor may not subcontract the management and general administration of the project and the Partners may not subcontract all or most of the activities for which they are responsible.

Subcontracting agreements worth more than € 10 000 must be put out to tender by the Contractor and their conclusion approved by the Partnership. Subcontracting may not account for more than 30% of the total cost of the project.

Translation costs are, in principle, allowed only for translations to and from the official languages of the European Union. However, translation of working documents to and from the languages of the associated countries is also eligible. Likewise, the translation of the project results into the languages of the associated countries is eligible solely for the purpose of disseminating these results.

Any other type of subcontracting cost, if justified, must be entered in these columns.

III.3 FINANCIAL MANAGEMENT OF THE PROJECT BY THE CONTRACTOR

III.3.1.	General remarks

As project selection is based on an overall assessment of each project, project management must cover the whole of the budget and costs incurred.

III.3.2.	Bank account

The account specified in the Agreement and to which the Leonardo da Vinci grant will be paid must satisfy the requirements set out in section II.2 of this Handbook.

Cash withdrawals from the account should be avoided and must in any case be substantiated by the corresponding bank documents (receipts, etc.).

III.3.3. 	Accounting system/internal control

Contractors must set up an analytical accounting system or an adequate internal system, which must make it possible to identify:

- the sources of project funding;

- project expenditure incurred during the contract period.

All transactions in the contract period relating to actual expenditure/income under the project must be recorded systematically using a numbering system specific to each European project.

As far as possible, the persons responsible for managing the project should not be the same as those responsible for its financial management.

III.3.4.	VAT, customs duties and other taxes on goods and services

Contractors must ascertain from the competent national authorities the provisions, rules and legislation governing the taxation of training activities in their countries.

VAT cannot, in any case, be charged to the project unless it is a final charge, i.e. a charge that is not deductible and cannot be recovered by the Contractor or the Partners.

Like VAT, other types of taxation, duty or charges which may arise from Community financing are eligible costs if they are actually and finally borne by the parties concerned.

III.3.5.	Exchange rates

As the amounts given in the reports must be expressed in euros, Contractors will have to carry out currency conversions. The exchange rates used to draw up the reports must be based on the exchange rates used for bank transactions.

Two types of situation may arise:

- for accounts in euros: the Contractor must enter the amounts debited in euros from its accounts;

- for accounts in national currencies, the Contractor must use the following rates.

Final reports for one-year contracts and interim reports

The Contractor must use the exchange rate applied by the bank to convert the first advance into national currency. If it cannot use this conversion method, it must able to state what exchange rate or rates have been used, and why.

Example:

| First advance (euros) | Bank rate | First advance (DKK) |
| --- | --- | --- |
| 40 000 | 7.5 | 300 000 |

The rate to be used to convert costs in DKK back to euros will therefore be 7.5.

Final reports for two-year contracts

For all costs incurred during the second 12-month period, whatever the source of the funds used, the Contractor must use the exchange rate applied by the bank to convert the second advance into national currency. If it cannot use this conversion method, it must be able to state what exchange rate or rates have been used, and why.

Example:

| Advances (euros) | Bank rate | Advances (DKK) |
| --- | --- | --- |
| First period | 40 000 | 7.5 | 300 000 |
| Second period | 40 000 | 7 | 280 000 |
| TOTAL: | = 80 000 |  | = 580 000 |

The rate to be used to convert costs in DKK back to euros during the second period will thus be 7.

The same method must used for  cross-rates.

Example:

| First advance (euros) | Bank rate | First advance (DKK) |
| --- | --- | --- |
| 40 000 | 7.5 | 300 000 |

Supposing that, during the first period, DKK 30 000 has been transferred to a Partner with a bank account in GBP (pounds sterling):

| Amount transferred in DKK | Bank rate | Amount converted into GBP |
| --- | --- | --- |
| 15 000 | 10.6125 | 1413.43 |
| 15 000 | 10.55 | 1421.80 |
| TOTAL: = 30 000 |  | = 2835.23 |

The rate to be used to convert expenditure in GBP during the first period back into DKK will be an average rate obtained by dividing the total expenditure in DKK by the corresponding sum in GBP, i.e. DKK 30 000 /GBP 2835.23 = 10.5811.

The rate to be used to convert expenditure in GBP during the first period back into euros will therefore be: 10.5811/7.5= 1.41.

Variations in exchange rates will not alter the Community grant.

III.3.6.	Payment of the grant

Payment arrangements and dates will be laid down in the Agreement.

However, for Contractors' information and to allow them to plan their budgets, it can be indicated that grant transfers will be made as follows:

- for twelve or eighteen-month projects: 70% on signature of the Agreement and 30% on receipt and acceptance of the final report;

- for twenty-four, thirty or thirty-six month projects: 40% on signature of the Agreement, 30% on receipt and acceptance of the interim report and 30% on receipt and acceptance of the final report.

IV. REPORTS

IV.1. GENERAL REMARKS

The evaluation procedure is a crucial phase of the project since it allows a review and qualitative and quantitative assessment of:

- the results achieved against the aims (as regards activities/products), with implications for the whole of the grant if results are unacceptable and for the lump sum for personnel costs  when results are very poor;

- the means used to achieve these results in relation to the revised budget (as regards the financial aspect of the operating and subcontracting costs).

As the interim and final reports are the main evaluation tools, they must provide as true a picture of the project as possible. Contractors are therefore advised to read the report forms  carefully, as soon as they receive them, so that they are familiar with the content and aware of the financial and accounting information required for their completion.

In each report, the various financial tables form a coherent whole: the figures must therefore be consistent. Before submitting the report, the Contractor must check that the entries satisfy this requirement, referring to the explanatory notes provided in the Administrative and Financial Handbook and in the form.

The amounts given in this form must be expressed in euros and rounded to the nearest whole number. Before submitting the reports, the Contractor must also check that the totals and sub-totals given are arithmetically correct.

IV.2. FORMAL REQUIREMENTS FOR ACCEPTANCE OF REPORTS

For a report form to be accepted and evaluated, the following formal requirements must be satisfied:

- The original of the form must be sent, together with a photocopy.

- The form must bear the original signature of the representative legally entitled to sign  of the contracting organisation. The representative’s name and position/title in the contracting organisation must be given below the signature, which must be accompanied by the organisation’s official stamp.

- The form must be returned in full (i.e. all its pages), duly completed and signed at the appropriate place.

- The financial report must be correctly completed according to the model, and presented in a consolidated form.

- The tables of transfers of funds must be completed by each member of the Partnership and must be original, dated, signed by the legal representative and stamped with the organisation’s official stamp.

- The following documents must be attached to the form:

-	Copies of the contracts concluded with the project Partners (including the Co-ordinator, if any). The Contractor must number these using the serial number allocated to each in the financial report.

-	Copies of any subcontracting agreements.

-	Copies of all invoices relating to subcontracting costs.

If the report does not meet the above criteria, the National Agency may not evaluate it until its formal presentation is correct.

IV.3. INTERIM REPORT

(for 24, 30 and 36-month contracts only)

IV.3.1. 	General remarks

The purpose of the interim report, relating to the first 12, 15 or 18 months depending on whether the contract is for 24, 30 or 36 months, is to take stock of progress at a "halfway point” and to pinpoint any specific problems that the Partnership has encountered so that action can be taken to allow the project’s main aims to be achieved as far as possible.

IV.3.2. 	Activity/results report

The first part of the interim report form is known as the activity/results report and is intended to provide a detailed picture of the project and its progress during the first period. It must therefore include at least the following information to allow a qualitative and quantitative assessment:

- 	a detailed report on the implementation and progress of the project, including a brief review of the roles of the various Partners in the various stages;

- 	an account of progress with the training products being prepared and any results already obtained, compared with the project aims as initially submitted;

- 	a brief description of products/results at this stage, with a copy if possible;

- 	information on any interaction or complementarity with other projects, programmes and/or networks;

- 	the internal evaluation procedure;

- 	measures to disseminate and transfer the results of the project, including, where applicable, measures for the legal protection of the project results;

- 	an account and explanation of the proposed roles of the various members of the Partnership as regards the intellectual property rights to the project and its results/products;

- 	a brief description of problems encountered;

- 	a work programme and account of proposed developments for the second period;

- 	a schedule of work carried out.

IV.3.3. Financial report

The second part of the interim report consists of a general balance sheet for the initial period and a financial estimate for the second period.

If the activity report demonstrates that the project is carried out according to the scheduled timetable, the analysis of the balance sheets will be moderate and only consist of checking that a certain level of expenses has been carried out. (It must be remembered that in the final report the promoter and its partners will have to give details on the expenses incurred during the whole duration of the project and provide the required information for the whole duration of the project).

If these two parts of the report  are provided, the second advance can be paid to the promoter.

IV.4.  FINAL REPORT

IV.4.1. 	General remarks

Since the purpose of the final report is to allow an overall evaluation of the project, all work must be completed before it is submitted.

IV.4.2. 	Activity/results report

The final report must be made on the form provided for the purpose, which will be sent to the Contractor in due course. It has a first section, known as the activity/results report and is intended to provide a detailed picture of the project. It must therefore include at least the following information to allow a qualitative and quantitative assessment:

- 	a one-page summary of the project developments/activities;

-	a one-page summary of the products/results achieved and completed;

- 	a detailed report on the implementation and progress of the project, including a brief review of the roles of the various Partners in the various stages;

- 	a description and two copies of the products/results, compared with the project aims as initially submitted;

- 	information on any interaction or complementarity with other projects, programmes and/or networks;

- 	the internal evaluation procedure;

- 	measures to disseminate and transfer the results of the project, including, where applicable, measures to protect the project results;

- 	an account and explanation of the proposed roles of the various members of the Partnership as regards the intellectual property rights to the project and its results/products;

- 	any plan for commercial exploitation agreed by the Partnership and involvement of  new Partners or other organisations in this activity;

-	a schedule of work carried out.

IV.4.3. Financial report

The second part of the final report consists of a balance sheet reporting expenditure over the entire project duration.

IV.4.4. 	Evaluation and monitoring

The National Agency reserves the right to suspend or reduce payment of the balance, or to require refunding of the Community funds, if the form and/or content of the final report does not conform with the Leonardo Da Vinci programme rules.

The consequences of the project results evaluation should also be borne in mind.

The final report will be evaluated by the National  Agency19 and by an independent external expert. This independent external expert will be designated by the Member State for procedure B and by the Commission for procedure C. The persons carrying out these evaluations will assign an overall rating, on a scale from 0 to 10, to the project results in the light of aims stated in the proposal.

If the rating awarded by the National Agency19 or external expert lies between 0 and 4, a further evaluation must be obtained from a second independent external expert.

If this is consistent with the previous evaluations, the following action will be taken:

- for ratings between 0 and 2 inclusive, the promoter will be required to repay the grant in full;

- for ratings between 3 and 4 inclusive, the lump sum for personnel costs will be reduced by 50%;

- for ratings between 5 and 10 inclusive, the promoter will be entitled to the full lump sum, as provided by the contract.

If the evaluations differ, the National Agency19 will determine unilaterally and definitively the final lump sum for personnel costs due to the promoter.

# IV.4.5.	Calculation of the final community grant

Where, after evaluation, the cost allowed in a particular budgetary column after deduction of any ineligible expenditure is lower than that envisaged in the Agreement, the financial evaluation may, in certain cases, give rise to:

- 	either a deduction from the final payment;

- 	or a repayment to the National Agency19, to an account opened for the purpose.

The Leonardo Da Vinci grant due to the promoter will be calculated as in the following example, which re-uses the figures already quoted to illustrate the grant allocation process.

In the following example it will be noted that the promoter provides information on the personnel costs. In any case, we invite promoters to provide this information,  for purely statistical purposes. As already explained, the personnel costs are not assessed according to the implementation and documentary proof, but according to the established lump sum and the project results.

|  | Budget estimate submitted by the promoter | Proposed estimated eligible expenditure | Community support | % |
| --- | --- | --- | --- | --- |
| A. Personnel costs |  |  |  |  |
| ISCO 1 | 52 350 | 50 705 |  |  |
| ISCO 210, 220 or 240 | 7 100 | 6 920 |  |  |
| ISCO 230 | 2 000 | 2 000 |  |  |
| ISCO 3 | 8 800 | 8.360 |  |  |
| ISCO 4 | 20 250 | 20 250 |  |  |
| Sub-total I | 90 500 | 88 235 | 57 000 |  |
| B. Operating costs |  |  |  |  |
| 1. Travel | 34 500 | 31 500 | 31 500 | 100% |
| 2. ICT | 20 000 | 20 000 | 20 000 | 100% |
| 3. Production | 5 000 | 5 000 | 5 000 | 100% |
| 4. Overheads | 13 500 | 13 500 | 0 | 0% |
| 5. Others | 0 | 0 | 0 | 0% |
| Sub-total II | 73 000 | 70 000 | 56 500 | 80.7% |
| C. Subcontracting costs |  |  |  |  |
| 1. Translation | 25 000 | 20 000 | 20 000 | 100% |
| Sub-total III | 25 000 | 20 000 | 20 000 | 100% |
| Total project cost | 188 500 | 178 235 | 133 500 | 74.9% |

When the contract was concluded, the promoter accepted the proposed estimated eligible expenditure and the amount and breakdown of Community support as a basis for achieving the aims specified in the project.

The project results evaluation by the National Agency and the external expert had a positive outcome.

|  | Proposed estimated eligible expenditure | Community support | % | Eligible (final report) | Community grant |
| --- | --- | --- | --- | --- | --- |
| A. Personnel costs |  |  |  |  |  |
| ISCO 1 | 50 705 |  |  | 54 360 |  |
| ISCO 210, 220 or 240 | 6 920 |  |  | 6 920 |  |
| ISCO 230 | 2 000 |  |  | 2 000 |  |
| ISCO 3 | 8.360 |  |  | 9 390 |  |
| ISCO 4 | 20 250 |  |  | 20 730 |  |
| Sub-total I | 88 235 | 57 000 |  | 93 400 | 57 000 |
| B. Operating costs |  |  |  |  |  |
| 1. Travel | 31 500 | 31 500 | 100% | 30 675 | 30 675 |
| 2. ICT | 20 000 | 20 000 | 100% | 21 135 | 21 135 |
| 3. Production | 5 000 | 5 000 | 100% | 3 950 | 3 950 |
| 4. Overheads | 13 500 | 0 | 0% | 13 500 | 0 |
| 5. Others | 0 | 0 | 0% | 0 | 0 |
| Sub-total II | 70 000 | 56 500 | 80.7% | 69 260 | 55 760 |
| C. Subcontracting costs |  |  |  |  |  |
| 1. Translation | 20 000 | 20 000 | 100% | 17 500 | 17 500 |
| Sub-total III | 20 000 | 20 000 | 100% | 17 500 | 17 500 |
|  | 178 235 | 133 500 | 74.9% | 180 160 | 130 260 |

The final Leonardo Da Vinci grant for the project is € 130 260, on the following basis:

- Since achievement of the project aims has been positively assessed, the lump sum of € 57 000 for personnel costs is allowed.

- Since travel and subsistence costs amount to € 30 675 and are 100% funded, Community support under this heading is € 30 675.

- At € 21 135, ICT costs  are less than 10% above the estimated eligible expenditure, and are 100% funded. Community support is therefore € 21 135.

- Production costs amount to € 3 950 and are 100% funded. Community support is thus € 3 950.

- Subcontracting costs are € 17 500 and are 100% funded, attracting Community support of  € 17 500.

If the amounts of Community support under the various budget headings were to add up to more than the maximum Community grant, in this case € 133 500, the final grant would of course be limited to € 133 500.

V.	AUDITS

V.1.	PURPOSE

As set out in the Agreement, an operational and/or financial audit can be carried out on the spot by the National Agency, the Commission or the Court of Auditors of the European Union. In such cases, Contractors will be notified that an inspection visit is to be made.

On receipt of this notification, Contractors are advised to ensure that all the original documentation likely to be examined by the auditors is available and, if necessary, contact their Partners in order to collect any original documents that may be missing. The audit will cover not only expenditure committed by the Contractor but also the costs borne by the whole of the Partnership.

The purpose of these audits is twofold: Firstly, to check that the project’s financial reports presented for payment are consistent with the Contractor’s basic accounts and to ensure that Community funds have been spent in accordance with the Agreement and its annexes, that the aims of the project have been achieved and that the products/results have been generated.

Secondly, audits provide a good opportunity for contact and dialogue between the auditors and the Contractor. If any management problems are found, the auditors will work with the Contractor to seek a solution and, if necessary, improve existing internal procedures in order to make the best possible use of Community funds. The auditors will be open to any comments and/or suggestions that the Contractor and the Partners may wish to make.

The main evaluation criterion is transparency, rather than strict compliance with contract rules. It is essential for the auditors to have access to full, accurate and properly documented information.

Lastly, the audit will cover the use of funds from all sources.

V.2.	DOCUMENTS REQUIRED

V.2.1.	General remarks

In principle, supporting documents must satisfy the following conditions if they are to be taken into consideration:

- they must be original and dated; documents from the Partners will of course be copies, the original being held by the Partner concerned;

- they must come from third parties and not have been produced internally, except in the cases discussed above.

Proforma invoices will not be accepted, except for expenditure committed and not yet paid, in which case the Contractor will have to provide proof of payment at a later date. For payments which have already been made, only final invoices will be accepted and the Contractor will have to be able to supply bank statements or other proof of payment.

As a general rule, the Contractor must provide the auditors with all bank documents. The contracting organisation’s accounting records, analytical accounts and annual statements must also be available.

In its agreements with the other members of the Partnership, the Contractor must require each member to supply the documents substantiating declarations of expenditure for the cost headings not covered by a lump sum. This will enable the Contractor to check the information it supplies in the various financial tables, for which it is responsible. The Contractor must be able to produce any supporting document asked for in connection with an audit or other request for information.

If the Contractor cannot provide adequate supporting documents for project-related expenditure or if the supporting documents available do not satisfy the requirements set out in this section, the auditors reserve the right to exclude the costs in question from total eligible expenditure.

The supporting documents required for each type of cost are described in the following paragraphs.

V.2.2.	Personnel costs

Since personnel costs are covered by a lump sum, promoters will not be required to produce supporting documents.

However, two cases must be distinguished: audits conducted during a project's life and audits after the project has been completed.

Audits during the project's life:

In this case, the promoter can demonstrate only that the project is proceeding as provided for in the contract and that the other costs (operating and subcontracting costs) prove that it is in progress.

Ex-post audits:

At this stage, the promoter can produce the project results. Auditors must contact the National Agency, which will provide them with a copy of the project results evaluation. They will also have access to the documents substantiating other costs (operating and subcontracting costs) to underpin their assessment of the lump sum.

V.2.3.	Travel and subsistence costs

Travel costs will be reimbursed as follows:

- for train travel: on the basis of original tickets;

- for air travel: on the basis of original tickets and boarding passes;

- for travel in a private vehicle: on the basis of a statement from the rail company or airline confirming the train or air fare for the journey;

- for travel in a hired vehicle: on the basis of the invoice;

- for taxi journeys: on the basis of the receipt and an expense form (or equivalent).

Subsistence costs, including accommodation and meals, will be reimbursed on a lump-sum basis and may exceed neither the daily rate per person applied by the organisation to which the person travelling belongs nor the maximum daily rate per person specified in the table in section III.2.3 of this Handbook.

V.2.4. 	Costs in connection with computer and audio-visual equipment

Invoices for hardware must be available.

In the case of connection costs, software and other kinds of computer and audio-visual costs, only actual, and not lump-sum, costs will be covered by the Leonardo da Vinci programme. This means that there must be a suitable system for identifying the costs arising from the use of computer equipment and that the Contractor must as far as possible provide the corresponding supporting documents.

V.2.5. 	Production costs

Invoices must be available.

V.2.6.	Overheads

Since overheads are covered by a lump sum which may amount to 7% of the total estimated project cost (which is thus fixed at the time of the tender and cannot change in the course of the project), no supporting documents need be produced.

V.2.7. 	Other costs

Here again, only actual costs as shown on the corresponding invoices can be charged to the project.

V.2.8.	Subcontracting costs

If Contractors use the services of a subcontractor, they must be able to produce the agreement concluded with the latter, the invoice(s) paid and any other supporting document connected with the subcontracting costs set out in the report. The Commission reserves the right not to accept all or part of such expenses if they do not satisfy the eligibility requirements set out in the Agreement.

V.3. FINDINGS AND OUTCOME

Contractors will be informed of the audit findings. These will be based on the transparency of the project and its general quality:

- The audit is entirely satisfactory.

- Some information/documents were not available at the time of the audit. The Contractor will then be asked to send them by post. Depending on the nature of the information/documents required, the outcome will be either as above or as below.

- Ineligible expenses have been found: these will entail either a reduction of the balance to be paid, or a demand for repayment to the Commission, depending on the amount involved and the time at which the audit is carried out.

Audit findings are internal Commission information and are confidential.

ANNEX 1 -	International Standard Classification of Occupations

(ISCO-88 (COM))

100	Legislators, senior officials and managers

110	Legislators and senior officials

111	Legislators and senior government officials

114	Senior officials of special-interest organisations

120	Corporate managers

121	Directors and chief executives

122	Production and operation managers

123	Other specialist managers

130	Managers of small enterprises

131	Managers of small enterprises

200	Professionals

210	Physical, mathematical and engineering science professionals

211	Physicists, chemists and related professionals

212	Mathematicians, statisticians and related professionals

213	Computing professionals

214	Architects, engineers and related professionals

220	Life science and health professionals

221	Life science professionals

222	Health professionals (except nursing)

223	Nursing and midwifery professionals

230	Teaching professionals

231	College, university and higher education teaching professionals

232	Secondary education teaching professionals

233	Primary and pre-primary education teaching professionals

234	Special education teaching professionals

235	Other teaching professionals

240	Other professionals

241	Business professionals

242	Legal professionals

243	Archivists, librarians and related information professionals

244	Social science and related professionals

245	Writers and creative or performing artists

246	Religious professionals

247	Public service administrative professionals

300	Technicians and associate professionals

310	Physical and engineering science associate professionals

311	Physical and engineering science technicians

312	Computer associate professionals

313	Optical and electronic equipment operators

314	Ship and aircraft controllers and technicians

315	Safety and quality inspectors

320	Life science and health associate professionals

321	Life science technicians and related associate professionals

322	Health associate professionals (except nursing)

323	Nursing and midwifery associate professionals

330	Teaching associate professionals

331	Primary education teaching associate professionals

332	Pre-primary education teaching associate professionals

333	Special education teaching associate professionals

334	Other teaching associate professionals

340	Other associate professionals

341	Finance and sales associate professionals

342	Business services agents and trade brokers

343	Administrative associate professionals

344	Customs, tax and related government associate professionals

345 	Police inspectors and detectives

346	Social work associate professionals

347	Artistic, entertainment and sports associate professionals

400	Clerks

410	Office clerks

411	Secretaries and keyboard-operating clerks

412	Numerical clerks

413	Material-recording and transport clerks

414	Library, mail and related clerks

419	Other office clerks

420	Customer services clerks

421	Cashiers, tellers and related clerks

422 	Client information clerks

# Footnotes

Annex 1 defines and details the personnel classification. ISCO : International Standard Classification of Occupations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The representative legally entitled to sign means the person authorised to enter into legal and financial commitments on behalf of the organisation to which he belongs.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The date on which the contract period ends must not be confused with the date of submission of the final report.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The rule of maximum variation of 10% and 5000 euros has to be understood as follows : if the variation is of 3500 euros on a budget of 10000 euros, it is acceptable because although higher than 10% it is lower than 5000 euros ; if the variation is of  7000 euros on a budget of  75000 euros, it is acceptable because although higher than 5000 euros its lower than 10%. In both cases a written amendment is not necessary.  An amendment must be asked and done if the variation is simultaneously more than 10% and 5000 euros.

Only the list of Partnership members as set out in the Agreement, subject to any amendments officially accepted by National Agency, is binding.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The data included in this table could change during the programme implementation. The updated versions will be sent to National Agencies and published on the Leonardo da Vinci website.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

This rule also applies if the translation is made by a member of the Partnership and the costs so incurred are charged against personnel costs.

The representative legally entitled to sign means the person authorised to enter into legal and financial commitments on behalf of the organisation to which he belongs..

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

The Commission for activities covered by procedure C: reference material, thematic actions, joint actions and projects of European organisations.

Eligibility will be checked for the budget headings which are not lump sums, namely travel and subsistence costs, information and communication technology costs, production costs, other costs and subcontracting costs.