ANNEXE 2.A

Work Programme

| Phase 1: Analysis of the situation of the enterprises |
| --- |
| STARTING DATE | December, 20th 2002 |
| END DATE | March, 20th 2003 |
| TOTAL DURATION | Three months |
| AIMS | To make a systematic situation analysis of the companies operating in selected sectors and operational partner contexts in order to know: Methods to determine the training needs in each firm, how and whether foreseen by company strategies; possible application of necessary instruments , or their programming possible planning methods of training courses methods and programming schedules for the introduction of additional professional figures methods of finding “training packages” and the professional figures necessary for their execution The analysis should arouse real interest for the companies involved in project activities |
| EXPECTED RESULTS | To reach a systematic and complete knowledge of the actual methods used to manage problems concerning professional training in the selected sectors and in the operational partner contexts To promote training activities and their programming (cross fertilisation) in the companies involved |
| PRODUCTS | First newsletter to present and promote project to sample firms Material and research kit Research result report on paper and also in hypertext published firstly on the partners’ WEB sites and later on the project site Second newsletter, which summarises the results and advertises their availability on the above mentioned supports, addressed to a wider audience: in the selected sectors and in the operational partner contexts, technical and vocational training schools in the partners’ areas, category associations, local institutions, etc. |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GREECE | POLAND |
|  | Organising videoconferencing among the partners | PLATFORM SERVINDUSTRIA PACINOTTI ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Sampling on the basis of adequate stratification of the whole project | ASSINDUSTRIA | ELKEDE | IPT |
|  | Drawing up and distribution of the first newsletter | ASSINDUSTRIA | ELKEDE | IPT |
|  | Elaboration of survey kit (targeted questionnaire) on paper and computerized and its translation into English | PLATFORM SERVINDUSTRIA PACINOTTI | _ | _ |
|  | Translation of the survey kit into the partners’ languages | _ | DEMOKRITOS | WSHE |
|  | Involvement of the sample companies by the category associations | ASSINDUSTRIA | ELKEDE | IPT |
|  | Direct or phone interviews with the involved firms | SUBCONTRACTING | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Data elaboration and ordering | PLATFORM SERVINDUSTRIA PACINOTTI | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Data drawing up and publication: On paper: publication of dedicated volume On computer: hypertext available on partners’ Web sites and later on the project site | PLATFORM SERVINDUSTRIA PACINOTTI | _ | _ |
|  | Organization and carrying out of the joint meeting for the project presentation, of its objectives and the results of the first phase to be held in Pistoia | PLATFORM SERVINDUSTRIA PACINOTTI ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Drawing and distribution of the second newsletter | ASSINDUSTRIA | ELKEDE | IPT |
| AIMS REACHING RATIOS | Existence of the above said products, in the scheduled time and with the required Characteristics Involvement of a proper number of companies enough to make a statistical sample. In order to extrapolate the necessary data to elaborate the instruments of the following phases ( for example, the participating companies that employ around 20% of the operators working in the local area in relevant sectors. Fulfilment of the quality indicators determined both in the process and in the product |
| DIFFUSION AND DISSEMINATION ACTIONS | Diffusion of the publications (report, newsletter) even through the involved category associations news bulletins and other publications addressed to companies ( CCIAA news bulletin, regional or local economic news bulletins of public institutions, etc) Partners’ joint meeting for project presentation, of its objectives and of the results of the first phase, to be held in Pistoia. Diffusion through press and mass media (television, local pages in national newspapers). Partners’ WEB sites. |
| EXTERNAL SUBJECTS INVOLVED AND THEIR ROLE | Office for the printing of the paper guides and of the newsletters. Institute specialized in translations into English. |
| QUALITY MANAGEMENT PLAN | By the end of each step the project aims to produce materials and documents which will be fundamental for the activation of the following phase; the intermediate results of the actions are thus continuously monitored and evaluated on the basis of their operating functionality for the starting of the next activity. Periodic monitoring and assessment activities are carried out by Servindustria Pistoia staff according to ISO9001 certification procedures, by means of special assessment check lists on behalf of the involved participants (project and companies’ staff). The above activities will deal with the process, supply, methods, instruments, organization, the invested economic resources and professionalism. Monitoring will be carried out by means of a functional control on the advancement state of the project. It will assess the efficiency, the pertinence of the developed activities with regard to the project objectives, deadlines and adequateness of the used methods. |

| Phase 2: Determining of leading companies |
| --- |
| STARTING DATE | March, 20th 2003 |
| END DATE | July, 20th 2003 |
| TOTAL DURATION | Two months, partially overlapping phases 3 and 8 |
| PRECONDITIONS | The carrying out of the previous phase should have aroused interest in the project which should be seen as a chance of development. The minimum requisite stated in the indicators of above said phase must be reached |
| AIMS | Select the most suitable companies for experimentation from the following points of view: Representiveness Availability Management motivation Interest in innovation |
| EXPECTED RESULTS | Selection of sample companies which represent the local company situation. Moreover these sample companies should be fairly interested in experimentation |
| PRODUCTS | Companies data base, on paper or on computer, which underline the necessary features to set up the instruments and products for the following ETP ( strategies, previous,present and future training, potential capacity. |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GREECE | POLAND |
|  | Meetings with the companies managers | SERVINDUSTRIA ASSINDUSTRIA | ELKEDE | IPT |
|  | Meetings with company people in charge of training/human resources | ASSINDUSTRIA SERVINDUSTRIA | ELKEDE | IPT |
|  | Drawing up and distribution of the first newsletter | ASSINDUSTRIA | ELKEDE | IPT |
|  | Elaboration of database | PLATFORM SERVINDUSTRIA PACINOTTI | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
| AIMS REACHING RATIOS | Existence of a sample of representative companies with the above indicators. These companies must employ at least 30% of the people contacted in the first phase |
| DIFFUSION AND DISSEMINATION ACTIONS | Newsletter about present and following activities addressed to companies of the selected sectors |
| EXTERNAL SUBJECTS INVOLVED AND THEIR ROLE | None |
| QUALITY MANAGEMENT PLAN | By the end of each step the project aims to produce materials and documents which will be fundamental for the activation of the following phase; the intermediate results of the actions are thus continuously monitored and evaluated on the basis of their operating functionality for the starting of the next activity. Periodic monitoring and assessment activities are carried out by Servindustria Pistoia staff according to ISO9001 certification procedures, by means of special assessment check lists on behalf of the involved participants (project and companies’ staff). The above activities will deal with the process, supply, methods, instruments, organization, the invested economic resources and professionalism. Monitoring will be carried out by means of a functional control on the advancement state of the project. It will assess the efficiency, the pertinence of the developed activities with regard to the project objectives, deadlines and adequateness of the used methods. |

| Phase 3: Orientation of Human Resource Managers |
| --- |
| STARTING DATE | June, 30th 2003 |
| END DATE | Sectember, 30th 2003 |
| TOTAL DURATION | Two months, partially overlapping phases 2, 4 and 8 |
| PRECONDITIONS | Reaching the objectives of the previous phase Availability of the necessary technical instruments |
| AIMS | Involvement of company managers and people in charge of human resources in order to: Let them find competence gaps with reference to company objectives Promote and improve their awareness of company training Let them discover the opportunities of company development related to the definition of ETP Increase their motivation towards the participating in the project |
| EXPECTED RESULTS | A successful involvement of managers in reaching stated objectives, above all the people in charge of human resources, in order to get them to improve their training culture and to promote, at the same time, the development of the project |
| PRODUCTS | Informing/vocational material, on paper or audiovisual (CD) support, in order to involve professional centres and jointly organize training and self-training cources in the companies. Study, planning and creation of a project Web site, where the elaborations of the previous and following phases will be published. Diffusion of the use of the Web as a virtual meeting/dialogue point on the subjects under discussion. |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GREECE | POLAND |
|  | Production and diffusion of the informative/vocational materials | SERVINDUSTRIA ASSINDUSTRIA PACINOTTI PLATFORM | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Meetings with company people in charge of training/human resources and managers | ASSINDUSTRIA SERVINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | WEB site implementation | PLATFORM SERVINDUSTRIA PACINOTTI | _________ | ______ |
|  | Online FAQ and tutoring | PLATFORM SERVINDUSTRIA PACINOTTI | _________ | _______ |
| AIMS REACHING RATIOS | The realisation of the stated products, by the deadlines and as required by the project At least 30% of the companies contacted in the first phase must have taken part in the project Product and process quality achievement must adhere to the indications set by the project |
| DIFFUSION AND DISSEMINATION ACTIONS | Newsletter which reports on the project progress, to be sent to the companies of selected sectors. Seminary for the diffusion of the stakeholders initiatives of local production. Web site |
| EXTERNAL SUBJECTS INVOLVED AND THEIR ROLE | Company specialized in the production of educational audiovisual aids |
| QUALITY MANAGEMENT PLAN | By the end of each step the project aims to produce materials and documents which will be fundamental for the activation of the following phase; the intermediate results of the actions are thus continuously monitored and evaluated on the basis of their operating functionality for the starting of the next activity. Periodic monitoring and assessment activities are carried out by Servindustria Pistoia staff according to ISO9001 certification procedures, by means of special assessment check lists on behalf of the involved participants (project and companies’ staff). The above activities will deal with the process, supply, methods, instruments, organization, the invested economic resources and professionalism. Monitoring will be carried out by means of a functional control on the advancement state of the project. It will assess the efficiency, the pertinence of the developed activities with regard to the project objectives, deadlines and adequateness of the used methods. |

| Phase 4: Analysis of the context partner Countries’ companies and elaboration of the instruments supported by information and communication technology |
| --- |
| STARTING DATE | September, 15th 2003 |
| END DATE | March, 31st 2004 |
| TOTAL DURATION | Four months, partially coinciding with phases 3, 5 and 8 |
| PRECONDITIONS | Reaching previous phases’ aims |
| AIMS | Identification of procedures for the elaboration of Firm Training Plans and creation of relevant models based on an analysis of the reference contest of the firms involved in the experimentation (insertion background, human, economical, structural and technological resources; goods, work and services market; current technologies; strategic choices; organisation; etc.), of professionals involved, of the country, the environment and productive reference contest, and aimed at the identification of the best firm training strategies and of the possible, and maybe distinguished, application modes in the firms. Realisation of executive instruments aimed at: analysis of training needs; identification of professionals lacks; planning and supply of fit training actions; planning of insertion and finding of professionals; The personalisation of the multimedial product prototype on behalf of individual partner countries; so that the return on a territorial/local level is granted starting from the active involvement of the economical and social world in the initial phase of the CD ROM predisposition. |
| EXPECTED RESULTS | Creation of procedures for the elaboration of ETP and of relevant models identified starting from the firm contest and aimed at the optimisation of the firm training strategy. Realisation of different instruments aimed at reaching the above mentioned aims, which correspond to the needs and problems put in evidence in previous phases. |
| PRODUCTS | Handbook, both on paper and information (hypertext) support, for self evaluation of firm contest by firm management. Software instrument (hypertext, multimedial, in PC ambient) of the procedures and models for the elaboration of ETP aimed at optimisation of firm training strategy equipped with: Guide and help both on line; Paper guide-handbook for use; Demo version, with concrete examples of ETP. The product is to be available in partners’ languages (Italian, Greek; Polish) and English, seen as vehicle language for the WEB. Paper instrument (handbook of self implementation and self evaluation). Newsletter availability of the product for the firms involved in the experimentation. |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GREECE | POLAND |
|  | Elaboration of specific questionnaires | PLATFORM SERVINDUSTRIA PACINOTTI | --- | --- |
|  | Carrying out of data collection c/o involved firms | PLATFORM SERVINDUSTRIA PACINOTTI ASSINDUSTRIA | --- | --- |
|  | Identification of optimal training strategies in that contest | PLATFORM SERVINDUSTRIA PACINOTTI ASSINDUSTRIA | --- | --- |
|  | Creation of procedures for the elaboration of aimed ETP for identified firms | PLATFORM SERVINDUSTRIA PACINOTTI | --- | --- |
|  | Analysis and verification with firms and with international partners (through a stay in Pistoia) of the products for their later implementation | PLATFORM SERVINDUSTRIA PACINOTTI ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Production of SW instrument and of its equipment in the indicated languages: Procedures plan Contents redaction Redaction of paper guides and limited printing for the experimentation Planning and graphic production SW development Demo version realisation CD ROM limited masterisation for experimentation and distribution | PLATFORM SERVINDUSTRIA PACINOTTI SUBCONTRACTING | ELKEDE KEK ELKEDE DEMOKRITOS (on the basis of proposed models and software but according to such identified specifics and in the native language) SUBCONTRACTING | IPT WSHE (on the basis of proposed models and software but according to such identified specifics and in the native language) SUBCONTRACTING |
|  | Production of the paper instrument in the mentioned languages (handbook of self implementation and self evaluation) | PLATFORM SERVINDUSTRIA PACINOTTI SUBCONTRACTING | ELKEDE KEK ELKEDE DEMOKRITOS (on the basis of proposed models and software but according to such identified specifics and in the native language) SUBCONTRACT | IPT WSHE (on the basis of proposed models and software but according to such identified specifics and in the native language) SUBCONTRACT |
|  | Meeting c/o one of the Greek partners in order to verify products functionality | PLATFORM SERVINDUSTRIA PACINOTTI | DEMOKRITOS ELKEDE KEK ELKEDE | --- |
|  | Meeting c/o one of the Polish partners in order to verify products functionality | PLATFORM SERVINDUSTRIA PACINOTTI | --- | IPT WSHE |
|  | Redaction of ETP examples aimed at a specific identified professionals | SERVINDUSTRIA ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | WSHE IPT |
|  | Redaction and distribution of the newsletter for the product availability for the firms involved in the experimentation | ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | WSHE IPT |
| AIMS REACHING RATIOS | Existence of mentioned products within provided times and quantity Fulfilment of identified quality ratios both in the process and in the product |
| DIFFUSION AND DISSEMINATION ACTIONS | Diffusion of product version realised in all its components (see PRODUCTS) through channel already used in the previous phases (diffusion channel of category associations/economical public organisation) and through the project WEB site. Newsletter availability of product, sent to all the firms in the identified sectors. Seminar for stakeholders’ sensitisation and involvement of category associations/economical public organisation Demo version diffusion through special WEB site and newsletter |
| EXTERNAL SUBJECTS INVOLVED AND THEIR ROLE | Category association. Economical public organisation (CCIAA). Translators for section in English. Typography for the printing of paper guides. |
| QUALITY MANAGEMENT PLAN | The project is structured in such a way as to provide at the and of each step the production of materials and documents fundamental for the activation of the next phase; consequently actions intermediate results are continually monitored and tested on the basis of the functionality to a further business starting. In itinere and ex post monitoring and testing activity is guaranteed by Servindustria Pistoia staff under the procedures of certification ISO9001, through evaluation specific check lists by involved actors (project staff and firms), in respect of the following different aspects: of process, logistic, methodological, instrumental, organisational, of invested economical resources and professionals. The monitoring will also be carried out by means of a functional instrument for the project implementation state check, time respect and adequacy of used methodologies. |

| Phase 5: Instruments focus with an on the spot text by means of an experimentation in pilot firms |
| --- |
| STARTING DATE | March, 15th 2004 |
| END DATE | December, 19th 2004 |
| TOTAL DURATION | Three months partially coinciding with phases 4, 6 and 8. |
| PRECONDITIONS | The phase begins after the elaboration of the instruments identified in phase 4 and the creation of a net of pilot firm in phase 2. |
| AIMS | This phase provides to sub-phases, whose aims are: A – first testing of experimental instruments, through which you have to identify problems and relevant practical solutions, supplied by the application of TICs to the instruments elaborated for productive sectors (craft, industry) and different market technologies areas (mechanical, agriculture, textile/clothing/footwear, information, etc); diffusion of the products addressed to experimentation, identification of firms with which to collaborate for the realisation of the sub-phase, help in the introduction in to the firm; B – subsequent change of instruments by operating on strong points in order to over come possible conceptual or structural weaknesses put in to evidence, in order to focus instruments and change them in to the final products to be diffused. |
| EXPECTED RESULTS | The phase can be considered concluded when: Predisposed instruments have been experimented and problematic aspects for products application have been put into evidence, especially with reference to different size and productive characteristics of the firm and to TIC approach. Involved firms have started an approach phase to ETP elaboration, through elaborated instruments and products, beginning in such a way the ? favoured by the project. Instruments strong and weak points have been put in to evidence for the solution of possible application problems and necessary changes have been introduced. |
| PRODUCTS | Experiment report for each firm, in which outstanding elements have been put in to evidence for possible change and focus. Experiment report distinguished as for sector/production, in which outstanding aspects are put in to evidence for necessary differentiation on an application level. Instruments and products (see phase 4) in their final version to be diffused (see subsequent phase6). |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GREECE | POLAND |
|  | Presentation of experimental instruments and products to the firms identified in phase 2 | ASSINDUSTRIA SERVINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Identification of a referent for each firm and his involvement in the experimentation | ASSINDUSTRIA SERVINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Start of instruments use through personalised tutoring activities and guided application, even on line | SERVINDUSTRIA PACINOTTI PLATFORM | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Implementation of an on line forum for the discovery of application problems of instruments and products and for products use (on line help) | SERVINDUSTRIA PACINOTTI PLATFORM | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Report elaboration and their diffusion through paper and on line newsletter | SERVINDUSTRIA PACINOTTI PLATFORM ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Implementation of instruments and products | PLATFORM | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
| AIMS REACHING RATIOS | Experimentation in the sectors and firms identified in phase 2. Referents and firms involvement and feed back of their experimental activities. Instruments use and results diffusion by involved firms and operators (visualisation on the counter of the web site which server the project). |
| DIFFUSION AND DISSEMINATION ACTIONS | Creation of the experimental group (firm reference + tutor) and step by step diffusion of the experimentation results. Sensitisation of non involved firm directly by means of phase advertising through newsletter/web site and local (town and regional) mass media. |
| EXTERNAL INVOLVED SUBJECT AND THEIR ROLE | Typography for paper guides printing in their final version. Service centre for video conference. Typography for text report. Services centres for CD ROM masterisation in their final version. |
| QUALITY MANAGEMENT PLAN | The project is structured in such a way as to provide at the and of each step the production of materials and documents fundamental for the activation of the next phase; consequently actions intermediate results are continually monitored and tested on the basis of the functionality to a further business starting. In itinere and ex post monitoring and testing activity is guaranteed by Servindustria Pistoia staff under the procedures of certification ISO9001, through evaluation specific check lists by involved actors (project staff and firms), in respect of the following different aspects: of process, logistic, methodological, instrumental, organisational, of invested economical resources and professionals. The monitoring will also be carried out by means of a functional instrument for the project implementation state check, time respect and adequacy of used methodologies. |

| Phase 6 : Creation of Company Training Schemes networks |
| --- |
| STARTING DATE | MAY, 15TH 2004 |
| END DATE | DECEMBER, 19TH 2004 |
| TOTALDURATION | Five months, with the phases 5, 7 and 8 running simultaneously. |
| PRECONDITIONS | To complete this stage it is necessary to have completed all of the previous stages. It is particuraly important that in the previous phases a group of motivated companies are selected to apply the Company Training Schemes and are drawn from different company types, sizes and product lines. |
| AIMS | Enlargement of user base from production (Companies) to instruction agencies (Schools, Professional Training centres, Educators) Creation of an interactive school-business network, through which project information is distributed (to be realized in phase 8) and form the basis to continue activities beyond the duration of the project Supply the instruments necessary for Life Long Learning |
| EXPECTED RESULTS | Besides reaching indicated results, we expect to: To promote within the PMI of the various productive and product types present in the area a new training culture, which motivates with a projectual logic the human resources present or to be inserted in the company. To elaborate instruments for the creation and duration in time of training and informative links (demand/oppurtunity) between Schools and the PMI. To impose a "branch" relationship of alternative training. |
| PRODUCTS | Implementation of a web site that functions as a "portal" to exchange requests/oppurtunity (training needs, work experience, intervention of experts in the productive and training world, etc.) and the diffusion of exchanges between schools and businesses ( links to various sites, both regional and local). |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GRECE | POLAND |
|  | Involvement, using suitable informative and awareness drives, of local companies. | ASSINDUSTRIA | ELKEDE | IPT |
|  | Assistance in indivualizing and informing reference figures within companies, on the basis of results from previous phases. | SERVINDUSTRIA PLATFORM PACINOTTI | KEK ELKEDE ELKEDE | WSHE |
|  | Involvement of local training centres within the territory (Scholastic Institutes,CFP,etc.), in selecting and involving reference point figures for relations with the world of production. | SERVINDUSTRIA PLATFORM PACINOTTI | KEK ELKEDE ELKEDE DEMOKRITOS | WSHE IPT |
|  | Study, design and realization of web site’s added functions in various languages (i.e. of partners and in English). | SERVINDUSTRIA PLATFORM PACINOTTI | KEK ELKEDE ELKEDE DEMOKRITOS | WSHE IPT |
|  | Creation of focus groups per sector/product type – through interactive and distance instruments ( web pages on project site, newsletter, etc) – made to determine training process and to create company training plans | SERVINDUSTRIA PLATFORM PACINOTTI | KEK ELKEDE ELKEDE DEMOKRITOS | WSHE IPT |
| AIMS REACHING RATIOS | Involvement of a reasonable number of companies and training parties , so as to cover at least 10% of the macro production sector/product type choosen in the local skills category. Product and process quality achievement must adhere to the indications set by the project |
| DIFFUSION AND DISSEMINATION ACTIONS | Newsletter which reports on the project progress, to be sent to the local companies, through the channels determined in the previous stages Involvement of the production stakeholders. Door to door awareness drives towards companies and training parties. |
| INVOLVED EXTERNAL SUBJECTS AND THEIR ROLE | Software house for the creation of WEB site Translation of the parts in English |
| QUALITY MANAGEMENT PLAN | By the end of each step the project aims to produce materials and documents which will be fundamental for the activation of the following phase; the intermediate results of the actions are thus continuously monitored and evaluated on the basis of their operating functionality for the starting of the next activity. Periodic monitoring and assessment activities are carried out by Servindustria Pistoia staff according to ISO9001 certification procedures, by means of special assessment check lists on behalf of the involved participants (project and companies’ staff). The above activities will deal with the process, supply, methods, instruments, organization, the invested economic resources and professionalism. Monitoring will be carried out by means of a functional control on the advancement state of the project. It will assess the efficiency, the pertinence of the developed activities with regard to the project objectives, deadlines and adequateness of the used methods. |

| Phase 7 : Diffusion instruments, introduction on line of results and promotion of school/work alternating experience |
| --- |
| STARTING DATE | JUNE, 15TH 2004 |
| END DATE | DECEMBER, 19TH 2004 |
| TOTALDURATION | Five months,partially overlapping the phases 6 and 8. |
| PRECONDITIONS | This phase complements and implements the previous phase, a part of which coincides once the companies and training parties are involved. |
| AIMS | Identification of the diffusive modalities more consistent with the various product/marketing areas and with the different educators. Creation of assistance modalities for the application of the instruments through FAD of the reference in the companies. Implementation in the web site of the project about the settling down of the common parts of the various partners ‘territories’. Implementation in the web site of the project related to the meeting of needs/formative opportunities between school and companies – on the basis of the business training plans. |
| EXPECTED RESULTS | In addition to the reaching of the shown objectives, it is also supposed to: promote in the PMI interested by the experimentation a new training culture, in order to stimulate in a projectual logical way an intervention in the existing human resources or new workers to be inserted in the company; create on the territory a diffused referral system for both companies and trainers, in order to develop the cooperation between the productive ‘world’, particularly the one of PMI, and the training one. Creation of an open system, and ready to be immediately used by the different subjects, in order to elaborate PFA, also through the assistace on- line of the project’s trained experts. Increase and create more conformity to the specific business training objectives on offer from the territorial training system. |
| PRODUCTS | CD Rom in DEMO format to show the opportunities offered by the project, with interactive links connected to the project “portale”, (worked on and implementated in the previous phase). Feed Back report through the research methods for product rating and the assistance in the introduction of PFA elaboration instruments. Translation of the Web site in several languages (the ones from partners + English for WEB) in which all the methodological apects necessary for the elaboration of PFA will be present. Methodology of company placement and of alternating from study/job on the basis of business training programs worked on through the present project. |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | . INVOLVED PARTNERS AND THEIR ROLES |
|  |  | ITALY | GREECE | POLAND |
|  | Production of DEMO and its diffusion | PLATFORM SUBAPPALTO | ELKEDE KEK ELKEDE DEMOKRITOS (translation and adaptation) | IPT WSHE (translation and adaptation) |
|  | Analysis of customer satisfaction, through a check list verified directly by telephone, and elaboration of a results report. | ASSINDUSTRIA SERVINDUSTRIA PACINOTTI | ELKEDE | IPT |
|  | Study, design and realization of the additional pages on the web site in the various langages (partners + English) | SERVINDUSTRIA PACINOTTI PLATFORM | DEMOKRITOS | WSHE |
|  | Individuation of the training assistance paths for companies. | SERVINDUSTRIA PACINOTTI PLATFORM | KEK ELKEDE | IPT |
|  | Individuation and involving of trainers for the creation of the interchange and needs/oppurtunities system. | SERVINDUSTRIA PACINOTTI | KEK ELKEDE | WHSE |
|  | Involving of the subjects (companies/trainers) and verified use of instruments and products . | ASSINDUSTRIA SERVINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
|  | Meeting of all partners in the headquarters of a Greek partner to verify completed actions . | SERVINDUSTRIA PACINOTTI PLATFORM ASSINDUSTRIA | ELKEDE KEK ELKEDE DEMOKRITOS | IPT WSHE |
| AIMS REACHING RATIOS | Reaching of a proper number of companies (for the coverage of at least 30% of assigned participants). Verification, through the check lists, to reach the target number of companies/assigned. Satisfaction of the quality indicators identified both in the process and in the product. |
| DIFFUSION AND DISSEMINATION ACTIONS | Public presentation of the product through the involving of the Category Assosiations and Economical Public Institution (Camera di Commercio I.A.A., Provincia, Comuni) Diffusion by mail of the CD Rom to all the companies. Diffusion through the local press and through the instruments of the various Category Assosiation (newsletters, etc.) of the phase instruments and products. Advertising of the website through e-mailing direct to companies of the different sectors identified in a territory. |
| INVOLVED EXTERNAL SUBJECTS AND THEIR ROLE | Category Assosiations. Economical Public Institutions and other Institutional Partners. Technological centre for the realization of the web site. Translation for the different parts of the site into English. |
| QUALITY MANAGEMENT PLAN | By the end of each step the project aims to produce materials and documents which will be fundamental for the activation of the following phase; the intermediate results of the actions are thus continuously monitored and evaluated on the basis of their operating functionality for the starting of the next activity. Periodic monitoring and assessment activities in itinere ed ex post are carried out by Servindustria Pistoia staff according to ISO9001 certification procedures, by means of special assessment check lists on behalf of the involved participants (project and companies’ staff). The above activities will deal with the process, supply, methods, instruments, organization, the invested economic resources and professionalism. Monitoring will be carried out by means of control on the advancement of the project. It will assess the efficiency, the pertinence of the developed activities with regard to the project objectives, deadlines and suitability of the methods used. |

| Fase 8 : Follow - up |
| --- |
| STARTING DATE | MARCH, 1ST 2004 |
| END DATE | DECEMBER, 19TH 2004 |
| TOTALDURATION | Eight months, partially placed at the end part of the previous phases. |
| PRECONDITIONS | Being a results diffusion phase for the entire project, its requisite is the final putting down of every aspect individuated in the previous phases. |
| AIMS | Reaching all participants eventually interested in implementating PFA. Diffusion of chances and opportunities offered by the introduction of PFA in the PMI. |
| EXPECTED RESULTS | Detailed information on the territory about the programming of PFA. Increasing training and alternation of study/job in PMI. Use of the project web site to verify and to make comparisions between user operators and implementation of the PFA. |
| PRODUCTS | Final project report , published on paper and in hypertextual format. Collection of newsletters and intermediate reports. |
| ACTIVITIES/ WORKING METHODS AND TECHNIQUES | Convention to promote results, in videoconferencing with the project partners in their territorial areas, in order to exchange respective experiences and realized applications. Elaboration of the book / report in hypertext of the experiences during the putting into operation of the project. Monitoring activity and follow up, phase by phase. |
| AIMS REACHING RATIOS | Information to the highest possible number of companies, in the local and regional areas, through the involvment of local and regional Sectors and also in association with the partners’s territory and their istitutional channels. Verification of the number of contacts collected by the web site through the access counter, both on the public part and on the sub-password (if implemented). |
| DIFFUSION AND DISSEMINATION ACTIONS | Convention. Videoconferencing with partners and experience interchange. Sending of copy of the text elaborated on by the Sector Associations / companies / Economical and Public Institutions. |
| INVOLVED PARTNERS AND THEIR ROLE | All partners are involved in the realization phase. |
| INVOLVED EXTERNAL SUBJECTS AND THEIR ROLE | Service Centre for videoconferencing. Printers for the text report. |
| QUALITY MANAGEMENT PLAN | By the end of each step the project aims to produce materials and documents which will be fundamental for the activation of the following phase; the intermediate results of the actions are thus continuously monitored and evaluated on the basis of their operating functionality for the starting of the next activity. Periodic monitoring and assessment activities in itinere ed ex post are carried out by Servindustria Pistoia staff according to ISO9001 certification procedures, by means of special assessment check lists on behalf of the involved participants (project and companies’ staff). The above activities will deal with the process, supply, methods, instruments, organization, the invested economic resources and professionalism. Monitoring will be carried out by means of control on the advancement of the project. It will assess the efficiency, the pertinence of the developed activities with regard to the project objectives, deadlines and adequateness of the used methods. |